## Slide 1: Distorted Metrics

## Slide 2: Distorted Metrics
The importance of minimizing metrics distortions from your process are discussed
Distortions for the following possibilities are presented:
  Poorly recorded effort numbers
  Use of “Gut-feel” predictions
  Inappropriate application of metrics
  Metrics collection techniques

## Slide 3: As we have seen…
Software projects are known for being over-scheduled, over-budget, yet still suffering from quality problems
Without some form of measurement on your current processes, estimates for future projects remain guesswork
Metrics can be used to help you learn more about the way your organization works
  Understand actual effort and time taken on each task
  Recognize when your product is sufficiently stable to ship
  Understand whether new processes are actually working or worth the effort

## Slide 4: But if we are collecting those metrics incorrectly…
Decisions on what and when something should be enhanced or modified may be biased
Overall project estimates can suffer
Despite adding effort into your newly-founded metrics program, it is important to remember:
  ACCURACY IN COLLECTION WILL AFFECT YOUR DECISIONS

## Slide 5: What Can Cause Metrics Distortions?
Poorly recorded effort numbers
Use of “Gut-feel” predictions
Inappropriate application of metrics
Metrics collection techniques
Notes: Generally speaking, relative goals are better than fixed goals, since they are more achievable.

## Slide 6: What Can Cause Metrics Distortions?
Poorly recorded effort numbers
  Many software companies have dropped any recording of hours
  This kills a very tangible learning opportunity
  Timesheets of some form are critical to estimate accurately
Use of “Gut-feel” predictions
Inappropriate application of metrics
Metrics collection techniques
Notes: Generally speaking, relative goals are better than fixed goals, since they are more achievable.

## Slide 7: IT Projects - Recent History
Most IT projects the past 15 years have required workers to work overtime
Much of that overtime has gone unrecorded and typically uncompensated for reasons like:
  “We’re working on something cool”
  “Yeah, but I got options!”
  “Dude, everyone’s working late!”
  Competition
  Outsourcing fears
Despite this added effort, it is also true that numerous IT projects:
  Get cancelled before completion
  Get completed but are disastrously late, over budget and/or full of holes
  Get completed only to see the business go bankrupt
Notes: Top reasons cited for “The American Work-Ethic”:
Greed
Guilt
Conformity
Fear
This generally maps to the items bulleted above

## Slide 8: Cause and Effect?
Deliberate inaccuracy in time-accounting and artificially low labour costs can be the primary causes for IT project failures and may contribute to an organization’s downfall
      *Gene Fellner, Unreported and Unpaid Overtime: Distorted Measurements and Formulas for Failure
There's a bottom-line reason most industries gave up crunch mode over 75 years ago: It's the single most expensive way there is to get the work done.
      *Evan Robinson, Why Crunch Mode Doesn’t Work: 6 Lessons

## Slide 9: Some Historical Perspective
When Henry Ford famously adopted a 40-hour workweek in 1926, he was bitterly criticized by members of the National Association of Manufacturers. But his experiments, which he'd been conducting for at least 12 years, showed him clearly that cutting the workday from ten hours to eight hours — and the workweek from six days to five days — increased total worker output and reduced production cost. Ford spoke glowingly of the social benefits of a shorter workweek, couched firmly in terms of how increased time for consumption was good for everyone. But the core of his argument was that reduced shift length meant more output.
      *Evan Robinson, Why Crunch Mode Doesn’t Work: 6 Lessons

## Slide 10: What about Overtime?
In small doses, over non-repetitive weeks, Overtime is not a bad thing
But, mental fatigue causes an abrupt drop-ff in both productivity and quality, so requests for overtime are best to recognize this fact
1909 statistical study showed this graph to be true:
Many US IT shops have no policies or procedures in place to discourage or uncover poor management practices in setting schedules
*Sidney Chapman, Hours of Labour (1909)
Notes: The math is explained here: http://www.igda.org/articles/erobinson_crunch.php
But basically, OY represents Value, and OX represents cost, so as costs increase, value or return from your worker starts to decrease, and eventually, (at point ‘b’) can start to become negative!

## Slide 11: Other reasons why
Automation of middle-management tasks
  Workers assigned to multiple projects so that nobody understands their “intended” workload
Archaic Management Principles
  Resources tapped at under 100% “must be an inefficiency”
  This results in requests for effort >100%
Management skeptical of expert findings
  History of poor-management is difficult to overcome
Generational-Effect
  “I had to go through it, so do you!”
  Management history creates a reluctance to believe there could be anything wrong with getting free work from their staff
Death Spiral
  Poor planning begets coding errors, which begets greater workloads, and so on….
Notes: Tax code has had an effect in North America as well – each added worker costs more than just their salary, so even paid overtime is considered a cheaper means to extend output
Economic predicitions are for a labour crunch starting ~2010 that will make employee churn around the year 2000 seem mild in comparison– so retaining workers will be a critical goal, and limiting overtime will become an important way to help!
So you need to start monitoring this now to be ready for 2010.

## Slide 12: How to avoid excessive overtime?
Key is in accuracy of creating project/feature estimations
Estimates need to be based on data from similar projects
Recording time-estimates to feature or feature-set level may be appropriate, whereas recording project-hours may be too vague
Consider quality metric data as additive information in order to anticipate development and testing effort required for future projects
  eg: “Similar work took 15 days, but DDR was also high, so this time, 18 days makes more sense.”

## Slide 13: Effort Collection – What to expect?
Recognize that the problem won’t be solved quickly
Expect estimates based on metrics to provide immediate help in some areas, but how to read the data effectively will take time
Feedback cycle needs to be in place over a number of projects to learn the techniques from which you can get the best results
Overlap of effort can often exist which can make recording of data difficult for your employees
What worked last year, is not the necessarily the same this year.
  You always need to consider:
    The code has changed
    People have changed
    Broader area of support now required
Aim for an estimate range rather than specific estimates, there is no one “perfect process”

## Slide 14: What Can Cause Metrics Distortions?
Poorly recorded effort numbers
  Many companies have dropped any recording of hours
  This kills a very tangible learning opportunity
Use of “Gut-feel” predictions
  “Those who cannot remember the past are condemned to repeat it” *George Santayana, Philosopher
  Remembering the past, is one thing, applying appropriate measurements from similar history is what you should aim for!
Inappropriate application of metrics
Metrics collection techniques
Notes: Generally speaking, relative goals are better than fixed goals, since they are more achievable.

## Slide 15: Art or Science?
Estimates of feature development and even software repairs should become a more scientific exercise, but recognize that “artistic” ability, or “expert knowledge” can still help
The science side needn’t require a complicated process
  Basically, if data exists for similar projects, or similar efforts on previous features, or fixes, that data should be referenced when making estimations
The “art” side is learned through experience
  Typically, the more recent experience will be more relevant
  Unfortunately, it is difficult to turn off your long-term historical knowledge, and this awareness may actually distort your estimations

## Slide 16: Suggestions for applying your “artistic impression”
Record your decisions
  Numbers can be interpreted differently by different people, so whatever “rules” are applied to convert your metrics to estimates, those “rules” should be recorded to help guide future estimates
Try to work with estimate ranges rather than fixed numbers
  Sales & Marketing may initially be uncomfortable with ranges, but will benefit from ranges which prove accurate, rather than having “fixed” dates which seem to perpetually slip
Don’t wait for post-mortems to see if your estimates are accurate.
  Learning ½ way through a job that an “adjustment” you applied looks to be off by 20% could help you correct what remains in the schedule to make your end-delivery estimate more accurate

## Slide 17: What Can Cause Metrics Distortions?
Poorly recorded effort numbers
  Many companies have dropped any recording of hours
  This kills a very tangible learning opportunity
Use of “Gut-feel” predictions
  “Those who cannot remember the past are condemned to repeat it” *George Santayana, Philosopher
  Remembering the past, is one thing, applying appropriate measurements from similar history is what counts!
Inappropriate application of metrics
  Applying data from other platforms or languages is generally not appropriate
Metrics collection techniques
Notes: Generally speaking, relative goals are better than fixed goals, since they are more achievable.

## Slide 18: Applying the wrong metrics
Using metrics from different languages or platforms generally not appropriate
  LOC for Java not the same as for C, for example
Try to back up assumptions with use of other metrics
  Eg: As we have seen previously, simply assuming existing complex code is an area to expect troubles may be presumptuous
    Such assumptions require secondary checking of other metrics
    Is this code relatively new, or well field-tested?
    Has there been significant churn of late?
Metrics from one project used in another must be used cautiously
  Many factors involved with software metrics
  People’s abilities and past experience is always different

## Slide 19: What Can Cause Metrics Distortions?
Poorly recorded effort numbers
  Many companies have dropped any recording of hours
  This kills a very tangible learning opportunity
Use of “Gut-feel” predictions
  “Those who cannot remember the past are condemned to repeat it” *George Santayana, Philosopher
  Remembering the past, is one thing, applying appropriate measurements from similar history is what counts!
Inappropriate application of metrics
  Applying data from other platforms or languages is generally not appropriate
Metrics collection techniques
  Collecting metrics doesn’t necessarily mean you are collecting them properly!
Notes: Generally speaking, relative goals are better than fixed goals, since they are more achievable.

## Slide 20: Metrics Collection – The right stuff?
It is more important that the data you collect from your software be focused, accurate and useful rather than be plentiful
Over-collection of data is fairly common when groups first start
  Use pre-defined objectives to minimize this problem
Apply validation into your process to ensure that the data you are collecting is being collected properly
Consistency in metrics like LOC is more important than worrying about different ways to measure them.
  Symbolic LOC is a more useful measure than Physical LOC

## Slide 21: Metrics Collection – What to count?
Monitor new defect counts, as well as overall Defect Density Rate
Be careful with Static-Analysis tools that you properly discount False Positives from the defect counts you use to make decisions
  Ie: When is it the right time to load data into your trending tool?
Utilize status settings to help properly quantify the groups of errors
  Critical defects deserve concern
  Don’t let a large volume of historical maintenance level defects drive your development process
    Such issues have survived for some time already and may only deserve attention when related areas are also being overhauled
  Consider whether a defect with a status setting, like “Fix in Later Release” should be counted in your current measurement or not?
Notes: DDR is important when looking at Critical defects, but may appear skewed if you pull in cosmetic issues which may be historically functional, just not following today’s coding practice.
Balance the desire to cleanup style errors against the costs involved
  Style and maintenance cleanup can be considered an investment which you hope brings returns you will never be able to see!

## Slide 22: Metrics Collection – Development vs. Fixes
Bug fixes from a previous release will often be applied to code being modified for the newest release.
  This will likely affect churn numbers
  If significant enough, it is beneficial to be able to isolate these metrics for the tasks involved.
  This may not always be possible.
  Roughly speaking:
    Release had 12000 new LOC
    However, 1000 LOC were applied due to do bug fixes
    Therefore, we’ll use 11000 LOC as our churn count for that release.
  For LOC, this may be acceptable, but for Function/File/Class churn numbers, may not be easily isolated.
  Over time, you can learn whether this exercise is worth consideration, and for which metrics

## Slide 23: Metrics Collection – Effort Recording
Effort recordings can be skewed for many reasons
  Historically no collection of time-sheets
  Unsure how to record time to features
  Where to record “general work”?
  Wearing many hats, so hard to break out hours used
  Hours by former members helping fix a problem may go undetected
  Unwilling to record actual time taken out of fear
  If not fully supported by management, some groups may be lax or less accurate than others, making data difficult to use
  Too much granularity will raise concern this adds to bureaucracy
This metric is extremely valuable, so a set of guidelines should be offered to ensure some consistency is obtained from this data
Management support for this effort should be advertised

## Slide 24: End of Module